TAYLOR’S UNIVERSITY

CONSTRUCTION PROCESS AND ACTIVITIES

BUILDING CONSTRUCTION 1 ARC1523

ASSIGNMENT 2 : JULY 2014

FARAH FARHANAH BINTI KASSIM KUSHAIRI

0317534

Building Construction 1 ARC1523

Assignment 2 : Construction Process and Activities(Individual)

Assessments (30%)

FARAH FARHANAH BT KASSIM - 0317534

Week 1 – Grading

Activity 1                     : Lot staking                                                                                                                Duration                      : 1 day                                                                                                                              Materials                     : nails, wooden pegs, planks, wooden stakes, Builder’s line                                                                                                                                 Equipment                   : hammer, measuring tape, theodolite, Dummy level                                                                                                                                            Skilled Workers           : Land surveyor, general workers                                                                                      Technical Information : outline and boundaries of excavation clearly defined for construction to proceed.

Site work

Activity 2           : Site Clearing                                                                                                                 Duration             : 7 days   ( day 2 – 8)                                                                                                                                  Materials            : -                                                                                                                                        Equipment          : Backhoe Loader, chainsaw, lorry truck

Skilled Workers : Backhoe Loader Operator, General workers, Lorry driver, structural engineer (consultancy)

Technical information : consult with specialists to precent unwanted occurences, clearing of all unnecessary items on site.

Week 2

Activity 1: Stake lot for excavation & rough grade lot

Duration : 2 days

Materials :  nail, wooden stakes

Equipment : Hammer, measuring tape, level

Skilled workers: general workers

Technical information: locating each corner on lot following dimensions of plan. Must be accurate. Backfilling of foundation walls and shaping the lot to reach desired grade level and to conform to design of approved surface drainage plan.

Activity 2                     : Excavation for foundation                                                                                                                  Duration                      : 5 days                                                                                                                            Materials                      : -                                                                                                                                        Equipment                   : excavator, compactor                                                                                                                                            Skilled Workers           : Excavator Operator, Compactor Operator                                                                                                Technical Information : Excavate to around 300mm of the top soil. Keep away or stored well for later reuse due to its high water retentive characteristics.

Activity 3 : Setting out of building boundary

Duration : 1 day

Materials: markers, stakes

Equipment: measuring tape,hammer

Skilled workers : surveyor

Technical information: To provide the exact location of each element.

Week 3

Activity 1  		: Layout pillings

Duration             	             : 1 days

Materials                    	: nails, wooden pegs, planks, stakes, Builder’s line                                                                                                                                 Equipment                  	: hammer, measuring tape, theodolite, Dummy level                                                                                                                                            Skilled Workers           	: Land surveyor, general workers                                                                                      Technical Information 	: Indicating location of piles according to grid.

Activity 2                    : Piling                                                                                                               Duration                      : 7 days                                                                                                                             Materials                     : Reinforced concrete piles, Concrete, Reinforcement, wooden formworks                                                                                                                                        Equipment                   : Hydraulic Piling Hammer, Rebar Bending machine, Boring Machine, cement concrete mixer                                                                                                                                             Skilled Workers           : Hydraulic Piling Hammer Operator, Boring Machine Operator, Rebar Bender, General construction workers                                                                                  Technical Information : pile heads are properly protected, head of piles should at all times be central with the hammer and piles shall not run out of position.

Week 4

Activity 1                    : Piling (continuous)                                                                                                        Duration                      : 7 days                                                                                                                              Materials                     : Reinforced concrete piles, Concrete, Reinforcement, wooden formworks                                                                                                                                        Equipment                   : Hydraulic Piling Hammer, Rebar Bending machine, Boring Machine, cement concrete mixer                                                                                                                                             Skilled Workers           : Hydraulic Piling Hammer Operator, Boring Machine Operator, Rebar Bender, General construction workers                                                                                  Technical Information : pile heads are properly protected, head of piles should at all  times be central with the hammer and piles shall not run out of position.

Week 5

Activity 1                  : Pile capping

Duration                    : 7 days                                                                                                                             Materials                   : Reinforced concrete piles, Concrete, Reinforcement, wooden formworks                                                                                                                                    Equipment                 : Hydraulic Piling Hammer, Rebar Bending machine, Boring Machine, cement concrete mixer                                                                                                                  Skilled Workers         : Hydraulic Piling Hammer Operator, Boring Machine Operator, Rebar Bender, General construction workers                                                                           Technical Information: because of different heights, cut pile below cap using hacker , remove rebar, then apply capping reinforcement.

Week 6

Activity 1                    : Pile capping

Duration                      : 7 days( continuous)                                                                                                                             Materials                     : Reinforced concrete piles, Concrete, Reinforcement, wooden formworks                                                                                                                                                Equipment                   : Hydraulic Piling Hammer, Rebar Bending machine, Boring Machine, cement concrete mixer                                                                                                                                    Skilled Workers           : Hydraulic Piling Hammer Operator, Boring Machine Operator, Rebar Bender, General construction workers                                                                           Technical Information : because of different heights, cut pile below cap using hacker , remove rebar, then capping reinforcement

Week 7

Activity 1                    : Stump from Pile caps                                                                                                                 Duration                      :  7 days                                                                                                                         Materials                     : Concrete, reinforcements, timber formworks,                                            Equipment                  : Concrete Vibrator, Rebar bending machine, table saw

Skilled Workers          : Carpenter, Bar Bender, General worker                                                                        Technical Information : to realign level of substructure to ensure the ground floor is leveled with other floors.

Week 8

Activity 1                    : Ground Beam

Duration                      : 7 days                                                                                                                      Materials                     : Concrete, reinforcements, timber formworks,                                                                      Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                                   Skilled Workers          : Carpenter, Rebar Bender, General worker                                     Technical Information :  ensure the amount of reinforcement to be used suits the specific loading requirement and able to withstand forces by compressible materials. Ground beams connect pile caps together and are leveled on stumps.

Week 9

Activity 1                    : Ground Beam

Duration                      : 7 days (continuous)

Materials                      : Concrete, reinforcements, timber formworks,

Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer

Skilled Workers           : Carpenter, Rebar Bender, General worker                                                        Technical Information : ensure the amount of reinforcement to be used suits the specific loading requirement and able to withstand forces by compressible materials. Ground beams connect pile caps together and are leveled on stumps.

Week 10

Activity                       : Ground floor slab (all floor after beam)                                                                                                                 Duration                      : 7 days                                                                                                                 Materials                     : Concrete, reinforcements, timber formworks, Damp Proof Membrane (DPM), Rigid Floor Insulation                                                                                               Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                           Skilled Workers           : Carpenter, Rebar Bender, General worker                                                  Technical Information : cast after beam, proceed to next construction during curing time, control moisture content in concrete.

Week 11

Activity                       : Ground floor slab (all floor after beam)                                                                                                                 Duration                      : 7 days                                                                                                                 Materials                     : Concrete, reinforcements, timber formworks, Damp Proof Membrane (DPM), Rigid Floor Insulation                                                                                               Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                           Skilled Workers           : Carpenter, Rebar Bender, General worker                                                  Technical Information : cast after beam, proceed to next construction during curing time, control moisture content in concrete.

Week 12

Activity                     : Ground Floor Columns

Duration                   : 5 Days                                                                                                          Materials                  : Concrete, reinforcement, timber formwork                                                                                             Equipment                : Concrete Mixer, Concrete vibrator, bar bending machine, table saw                                                                                                                                                   Skilled worker             : Carpenter, bar bender, general worker                                                       Technical information : Columns are left to properly cure.  Extend the length of columns rebar to serve as starter bar for columns above.

Week 13

Activity                    : Ground Floor Columns

Duration                      : 6 Days( continuous)                                                                                                          Materials                     : Concrete, reinforcement, timber formwork                                                                                             Equipment                   : Concrete Mixer, Concrete vibrator, bar bending machine, table saw                                                                                                                                                   Skilled worker             : Carpenter, bar bender, general worker                                                       Technical information : Columns left to cure thoroughly. Extend the length of columns rebar to serve as starter bar for columns above.

Week14

Activity                     : First Floor Beam

Duration                      : 7 days                                                                                                               Materials                     : Concrete, reinforcements, timber formworks,                                            Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                            Skilled Workers          : Carpenter, Rebar Bender, General worker                                                  Technical Information :  Ensure proper curing takes place to be able to withstand load.

Week 15

Activity 1                     : First Floor Beam

Duration                      : 6 days  (continuous)                                                                                                                    Materials                     : Concrete, reinforcements, timber formworks,                                                                      Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                                   Skilled Workers          : Carpenter, Rebar Bender, General worker                                     Technical Information : ensure proper curing to take place so that it can withstand the load.

Activity 2                      :  Ground floor door framing

Duration                       : 2 days

Materials                      : aluminium door frame, shims, screws, rigid sill

Equipment                   : tape measure,level,hammer,screwdriver

Skilled workers            : general workers

Technical information :   The rough opening to be no less than 19 mm larger than the door unit in width and height. Ensure that the rough opening is level and square, and that the walls in the opening are not twisted.

Week 16

Activity                        : First Floor slab ( All after beam)

Duration                      : 7 days                                                                                                                 Materials                     : Concrete, reinforcements, timber formworks, Damp Proof Membrane (DPM), Rigid Floor Insulation                                                                                               Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                           Skilled Workers           : Carpenter, Rebar Bender, General worker                                                  Technical Information : cast after beam, proceed to next construction during curing time.

Week 17

Activity  1                      : First Floor slab

Duration                      : 7 days   (continuous)                                                                                                           Materials                     : Concrete, reinforcements, timber formworks, Damp Proof Membrane (DPM), Rigid Floor Insulation                                                                                               Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                           Skilled Workers           : Carpenter, Rebar Bender, General worker                                                  Technical Information : cast after beam, proceed to next construction during curing time.

Week 18

Activity 1                      : opening for stairs

Duration                      : 3 days

Materials                     :-

Equipment :

Skilled workers            : general workers

Technical information: ensure the opening is compatible for the stairs.

Activity 2                      : First Floor Column

Duration                      : 6 days

Materials                     : Concrete, reinforcement, timber formwork                                                                                             Equipment                   : Concrete Mixer, Concrete vibrator, bar bending machine, table saw ,hammer                                                                                                                                                  Skilled worker             : Carpenter, bar bender, general worker

Technical information: Allow for proper curing. Extend the length of columns rebar to serve as starter bar for columns above.

Week 19

Activity                        : First Floor Column

Duration                      : 6 days (continuous)

Materials                     : Concrete, reinforcement, timber formwork                                                                                             Equipment                   : Concrete Mixer, Concrete vibrator, bar bending machine, table saw ,hammer                                                                                                                                                  Skilled worker             : Carpenter, bar bender, general worker

Technical information: Allow for proper curing. Extend the length of columns rebar to serve as starter bar for columns above.

Week 20

Construction Activity : Staircase from ground floor to first floor.

Duration: 1 week

Materials: Framing lumber, Plywood, Wooden stakes/braces, Reinforcement, Concrete grade 35, Sand or gravel (for fill)

Equipment: Circular/hand saw, Drill, impact drill driver, Hammer, Double headed nails, Power mixer, Tape measure, String level, Finishing magnesium trowel, Wood float, Edger, Oil or release agent

Technical information:

- Building and assembling the forms - Lumber and plywood is cut according to planned dimension of steps, braced firmly in place to stakes set in the ground. Interior surfaces of formwork are then coated with oil or release agent to ease removal.

- Reinforcing steps – Holes are drilled into concrete foundation into which rebars are hammered in.

- Pouring concrete – Low areas in the forms are filled with sand or gravel to reduce amount of concrete needed, then concrete is poured into the formwork and mixed thoroughly with the aggregate. Concrete mix is then compacted with a shovel to eliminate air pockets.

- Screeding and levelling – Surface is screed immediately after compacting then levelled with a wooden float. After the surface has turned dull, an edger is used to round the edges. Finally the concrete is smoothed with a magnesium trowel to produce a textured non-skid surface.

- Finishing – A concrete broom dipped into water is lightly pulled across the surface for the desired finish.

- Curing – After at least 24 hours, the side forms are removed and surface of steps are lightly sprayed with water until it is entirely covered. Next, entire staircase is covered with plastic to prevent evaporation and allow the curing process to run for at least a week.

- Drying – After a week, the plastic is removed and steps are allowed to air dry for a further 7 days before us

Week 21

Activity                       : Second floor beam

Duration                      : 6 days                                                                                                                      Materials                     : Concrete, reinforcements, timber formworks,                                                                      Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                                   Skilled Workers          : Carpenter, Rebar Bender, General worker                                     Technical Information : ensure proper curing to take place so that it can withstand the load.

Week 22

Activity 1                     : Second floor beam

Duration                      : 6 days                                                                                                                      Materials                     : Concrete, reinforcements, timber formworks,                                                                      Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                                   Skilled Workers          : Carpenter, Rebar Bender, General worker                                     Technical Information : ensure proper curing to take place so that it can withstand the load.

Activity 2                       	: First Floor Door framing

Duration                      	: 2 days

Materials                     	: aluminium door frame,shims, screws, rigid sill

Equipment                       : tape measure, level, hammer, screwdriver

Skilled workers                : general workers

Technical information      :   The rough opening to be no less than 19 mm larger than the door unit in width and height. Ensure that the rough opening is level and square, and that the walls in the opening are not twisted.

Week 23

Activity                        : Second floor slab

Duration                      : 7 days

Materials                     : Concrete, reinforcements, timber formworks, Damp Proof Membrane (DPM), Rigid Floor Insulation                                                                                               Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                           Skilled Workers           : Carpenter, Rebar Bender, General worker                                                  Technical Information : cast after beam, proceed to next construction during curing time.

Week 24

Activity 1                      : Second floor slab

Duration                       : 7 days

Materials                     : Concrete, reinforcements, timber formworks, Damp Proof Membrane (DPM), Rigid Floor Insulation                                                                                               Equipment                   : Concrete Vibrator, Rebar bending machine, table saw, concrete mixer                                                                                                                                           Skilled Workers           : Carpenter, Rebar Bender, General worker                                                  Technical Information : cast after beam, proceed to next construction during curing time.

Activity 2                    	: Second Floor Door framing

Duration                      	: 2 days

Materials                     	:  aluminium door frame,shims, screws, rigid sill

Equipment                       : tape measure, level, hammer, screwdriver

Skilled workers                : general workers

Technical information      :  The rough opening to be no less than 19 mm larger than the door unit in width and height. Ensure that the rough opening is level and square, and that the walls in the opening are not twisted.

Week 25

Activity                        : second floor columns

Duration                      : 6 days

Materials                     : Concrete, reinforcement, timber formwork                                                                                             Equipment                   : Concrete Mixer, Concrete vibrator, bar bending machine, table saw ,hammer                                                                                                                                                  Skilled worker             : Carpenter, bar bender, general worker

Technical information: Allow curing to happen properly. Extend the length of columns rebar to serve as starter bar for columns above.

Week 26

Activity                        : second floor columns

Duration                      : 6 days (continuous)

Materials                     : Concrete, reinforcement, timber formwork                                                                                             Equipment                   : Concrete Mixer, Concrete vibrator, bar bending machine, table saw ,hammer                                                                                                                                                  Skilled worker             : Carpenter, bar bender, general worker

Technical information: Allow curing to happen properly. Extend the length of columns rebar to serve as starter bar for columns above.

Week 27

Activity                         : Stairs from first floor to second floor

Duration                       : 7 days

Materials                      : concrete, reinforcement, timber formwork

Equipment                   : concrete mixer, spade, steel trowel, hammer

Skilled worker              : bar bender, general worker, carpenter

Technical information  : keep the concrete wet or damp for up to one week while it cures and remove the form lumber after concrete attained final shape.

Week 28

Activity : Pitched Roof

Duration : 7 days

Materials: roof trusses, clay roof tile, wooden joists, wooden lath, nails, breathable membrane,mortar

Equipment: hammer ,chalk line,tin snips,clean up tools, trowel

Skilled workers: general workers,carpenter

Technical information: Hot dipped galvanized or stainless steel nails are used due to ability to withstand moist conditions. Overlying tiles should form interlocking configuration with first layer.

Week 29

Activity : Pitched Roof

Duration: 6 days (continuous)

Materials: roof trusses,clay roof tile, wooden joists, wooden lath, nails, breathable membrane,mortar

Equipment: hammer,chalk line,tin snips,clean up tools,trowel

Skilled workers: general workers,carpenters

Technical information: Hot dipped galvanized or stainless steel nails are used due to ability to withstand moist conditions. Overlying tiles should form interlocking configuration with first layer.

Week 30

Activity                        : Ground Floor Wall

Duration                      : 7 days

Materials                     : cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : laying of  brick wall with running bond, ensure that every brick is at the same level.

Week 31

Activity                        : Ground Floor Wall

Duration                      : 7 days (continuous)

Materials                     : cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : laying of  brick wall with running bond, ensure that every brick is at the same level.

Week 32

Activity                        : Ground Floor Wall

Duration                      : 7 days (continuous)

Materials                     : cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : laying of  brick wall with running bond, ensure that every brick is at the same level.

Week 33

Activity                     :  First Floor Wall

Duration                      :  7 days

Materials                     : cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : using running bond for bricks laying,ensure that every brick is at the same level.

Week 34

Activity                     :  First Floor Wall

Duration                      :  7 days    (continuous)

Materials                     : cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : using running bond for bricks laying,ensure that every brick is at the same level.

Week 35

Activity                     :  First Floor Wall

Duration                      :  7 days    (continuous)

Materials                     : cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : using running bond for bricks laying,ensure that every brick is at the same level.

Week 36

Activity : Second floor wall

Duration: 7 days

Materials: cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : using running bond for bricks laying,ensure that every brick is at the same level.

Week 37

Activity : Second floor wall

Duration: 7 days

Materials: cement sand bricks ,mortar, cement sand plaster

Equipment                  : trowel,spirit level,hammer and chivel

Skilled workers           : General workers

Technical information : using running bond for bricks laying,ensure that every brick is at the same level.

Week 38

Activity : Railing installation (stairs &balcony)

Duration : 5 days

Materials : posts, aluminium railing, anchor bolt, base plate, screws, top cap, brackets

Equipment: measuring tape, drill, Mitre saw, drill bits

Skilled workers: general workers

Technical information: When installing Posts, start with the outside or corner Posts first. Make sure they are plumb and level then install the intermediate Posts. Do not over torque screws when fastening bracket to post as this may cause post sleeve to crack.

Week 39

Activity                     	           : Windows

Duration                      	: 6 days

Materials                     	: aluminium frame, glass  window, screws,  nails,  shims

Equipment                   	:  hammer, level, drill with drill bits,  screwdriver  ,caulking

Skilled Workers           	:  general workers

Technical Information  : Use your level on the bottom sill and verify that the wall opening is level.

Week 40

Activity : Windows

Duration: 6 days (continuous)

Materials: aluminium frame, glass  window,screws,  nails,  shims ,

Equipment                   	:  hammer, level, drill,  drill bits, screwdriver  ,caulking

Skilled Workers           	:        general workers

Technical Information 	: Use your level on the bottom sill and verify that the wall opening is level.

Week 41

Activity                    	           : Door installation (ground floor)

Duration                      	: 5 days

Materials                     	:  timber door, hinges, srews, lock

Equipment                   	:  chisel, claw hammer,   spirit level,  measuring tape, screwdriver ,trimming knife  ,drill, drill bits

Skilled Workers           	:    general workers,carpenter

Technical Information 	:  A maximum 3mm may be trimmed from any edge. Wedge your door in the opening in the correct position and allow 3mm margins between door and jamb.

Week 42

Activity                    	           : Door installation   (first floor and second floor)

Duration                      	: 5 days (continuous)

Materials                     	:  timber door, hinges, srews, lock

Equipment                   	:  chisel, claw hammer,   spirit level,  measuring tape, screwdriver ,trimming knife  ,drill, drill bits

Skilled Workers           	:    general workers,carpenter

Technical Information 	:  A maximum 3mm may be trimmed from any edge. Wedge your door in the opening in the correct position and allow 3mm margins between door and jamb.

Week 43

Activity: Exterior finishes

Duration 7 days

Materials: lime ,sand ,water

Equipment: large bucket, wheelbarrow, trowel, garden hose

Skilled workers: general workers

Technical information: Apply the render to the wall as forcefully as possible to ensure that it keys into the wall well. Once the first coat of render is applied but not yet set, scratch the surface throughout the wall to provide a key for the next layer to adhere to. Best done on cool and cloudy day.

Week 44

Activity: Exterior finishes

Duration : 7 days (continuous)

Materials: lime ,sand ,water

Equipment: large bucket, wheelbarrow, trowel, garden hose

Skilled workers: general workers

Technical information: Apply the render to the wall as forcefully as possible to ensure that it keys into the wall well. Once the first coat of render is applied but not yet set, scratch the surface throughout the wall to provide a key for the next layer to adhere to. Best done on cool and cloudy day.

Week 45

Activity                          : Tiling

Duration                      	: 7 days

Materials                     	:     ceramic tiles,tile adhensive  ,water

Equipment                   	:    level,measuring tape,notched trowel,grout float  ,tile cutter ,sponge

Skilled Workers           	:   general workers

Technical Information 	: Keep installing tiles by lining them up and pressing them firmly. Once you have reached the edges of the area where you applied the tile adhensive, repeat the process by applying another equal-sized area and applying about 8 more tiles. This process keeps the mortar from curing too quickly.

Week 46

Activity                                   : Tiling (continuous)

Duration                                 : 7 days

Materials                     	:     ceramic tiles,tile adhensive  ,water

Equipment                   	:    level,measuring tape,notched trowel,grout float  ,tile cutter ,sponge

Skilled Workers           	:   general workers

Technical Information 	: Keep installing tiles by lining them up and pressing them firmly. Once you have reached the edges of the area where you applied the tile adhesive, repeat the process by applying another equal-sized area and applying about 8 more tiles. This process keeps the mortar from curing too quickly.

Week 47

Activity                    	            :Drywall on brick walls (ground floor)

Duration                      	: 5 days

Materials                     	:  plasterboard  , fiberglass tape,  screw ,base wood stud,construction adhensive ,nails ,joint compound

Equipment                   	:  drill, sledgehammer,sandpaper

Skilled Workers           	:    General workers

Technical information    :  The goal of sanding the areas is to remove any high spots of compound as well as to make the edge of the compound blend into the wall so it is not detected when painted.

Week 48

Activity                    	            : Drywall on brick walls (first floor)

Duration                      	: 5 days (continous)

Materials                     	:  plasterboard  , fiberglass tape,  screw ,base wood stud,construction adhensive ,nails ,joint compound

Equipment                   	:  drill, sledgehammer,sandpaper

Skilled Workers           	:    General workers

Technical information    :  The goal of sanding the areas is to remove any high spots of compound as well as to make the edge of the compound blend into the wall so it is not detected when painted.

Week 49

Activity                    	            : Drywall on brick walls (second floor)

Duration                      	: 5 days (continous)

Materials                     	:  plasterboard  , fiberglass tape,  screw ,base wood stud,construction adhensive ,nails ,joint compound

Equipment                   	:  drill, sledgehammer,sandpaper

Skilled Workers           	:    General workers

Technical information    :  The goal of sanding the areas is to remove any high spots of compound as well as to make the edge of the compound blend into the wall so it is not detected when painted.

Week 50

Activity                    : Painting

Duration                  : 7 days

Materials                 :  Nippon paint, masking tape

Equipment                   	:   broad putty knife,paint scrapper, long handled brush ,scrub brush,sandpaper ,sanding block,roller,brush comb,paint pail

Skilled Workers           	:    General workers

Technical information : Before painting, always prime the drywall to provide a coat for the paint to adhere to and to help give a more even appearance.Let the paint dry at least 2 or 3 hours before proceeding to the next coat.

Week 51

Activity          : Painting

Duration: 6 days (continuous)

Materials :Nippon paint ,masking tape

Equipment                   	:   broad putty knife,paint scrapper, long handled brush ,scrub brush,sandpaper ,sanding block,roller,brush comb,paint pail

Skilled Workers           	:    General workers

Technical information    :  Before painting, always prime the drywall to provide a coat for the paint to adhere to and to help give a more even appearance.Let the paint dry at least 2 or 3 hours before proceeding to the next coat.

Week 52

Activity: Car porch

Duration: 7 days

Materials: concrete slab,ceramic tiles,timber formwork,caulk,tile adhensive,sealer

Equipment : level,trowel,tile cutter,grout float, rounded putty knife,cloth

Skilled workers: general workers ,carpenters

Technical Information : make sure the slab is leveled. Seal expansion joints with caulk after cleaning them out well. Allow concrete to cure properly.

Week 53

Activity 1                  	: Paint touch up

Duration                      	: 5 day

Materials                     	: Nippon paint

Equipment                              :   long handled brush,roller,sandpaper,sanding block,scrub brush

Skilled Workers           	:  General workers

Technical Information 	: final touch up for the walls and ceiling paint,ensure the paint is evenly brushed.

Activity 2 : Cleaning

Duration : 5 days

Materials:-

Equipment:broom,vaccum,mop

Skilled workers : cleaners

Technical information: cleaning up the bungalow and hand over to owner.